## Slide 1: Developing a crime prevention project

## Slide 2: Developing a crime prevention project…. It’s More difficult than it seems

## Slide 3: Developing a crime prevention project…. It’s More difficult than it seems
Every idea behind a project may be based on good intention, but…
When it comes time to ACTUALLY DOING CRIME PREVENTION, it takes….

## Slide 4: Developing a crime prevention project…. It’s More difficult than it seems
A very long-term vision and sustainability plan,
Concrete, detailed, well thought-out plan that has clear and realistic goals,
A plan based on the technical side of crime prevention,
Capacity and resources (human and capital),
Good information,
Different types of partners,
Major intervention,
Ongoing evaluation to make adjustments,
Ongoing community input and buy-in,
Ongoing support for staff to prevent burn-out, high turn-over,
Ongoing building of self-value/worth,
Knowledge transfer.

## Slide 5: In order to develop a good crime prevention project we first need to…
Understand WHAT IS CRIME PREVENTION

## Slide 6: What is Crime prevention?
It is not just about an act of violence, but about all factors surrounding it.

## Slide 7: What is Crime prevention?

## Slide 8: What is Crime prevention?
Crime prevention is about understanding the causes of crime and violence.
Crime prevention is about understanding WHY:
Option 1. A crime is committed
Option 2. Someone is at risk of committing a crime or re-offending
Option 3. Someone is at risk of being a victim.

## Slide 9
Risk factors help us to understand some of the reasons behind why a crime is committed, why someone is at-risk of committing a crime (or re-offending) or being a victim
The goal is to...
Risk factor

## Slide 10: Examples of risk factors
Risk factors in Nunavik:
  Substance abuse
  Low literacy
  Poverty
  Unemployment /underemployment
  Lack of housing
  Lack of positive role models / lack of parenting skills
  Family violence
  Low self-esteem
  Transition out of institutional care (e.g. hospital, foster care, correctional facility)

## Slide 11: How do you know your project is crime prevention?

## Slide 12: How do you know your project is crime prevention?
  First-level (primary crime prevention)
This is also called “Social crime prevention”.
It focuses on changing social factors that lead to crime like poor parenting, poverty, behaviour problems (lack of self-control, problem solving skills, judgment), lack of employment and training, poor education.
Some examples :
Developing parenting skills
School programs for preventing youth at-risk of dropping out of school or addressing school violence
Early childhood programs for neglected children and their parents

## Slide 13: How do you know your project is crime prevention?
  Second-level (secondary crime prevention)
Focuses on changing people’s behaviours to prevent them from being a victim or committing a crime.
Some examples include:
  Substance abuse treatment program
  Services for abused women
  Mental health services

## Slide 14: How do you know your project is crime prevention?
Third-level (tertiary crime prevention)
Focuses on preventing re-offending. This type of crime prevention can involve the criminal justice system.
Some examples include:
  Training or employment programs for offenders in prison and those leaving prison
  Rehabilitation programs for ex-offenders
  Follow-up support services for individuals leaving substance abuse treatment centres (after-care)

## Slide 15: How do you develop a crime prevention project? What are the key elements?
Well-defined problem supported by information:
What are the main issues related to crime and violence in your community/region?
What are the causes behind the issues?
What is needed to address these issues?
What informal and formal services and programs exist in your community already? [Do a mapping exercise]
Are there any missing services and programs?

## Slide 16: How do you develop a crime prevention project? What are the key elements?
What are the risk factors causing these issues?
What are the deeper issues behind those risk factors?

## Slide 17: Now what?
We need to find out WHAT IS NEEDED to remove the risk factors and make that person feel better and to make his/her environment a better place.
KNOWLEDGE IS POWER

## Slide 18: How do you develop a crime prevention project? What are the key elements?
What information has been collected to prove that these are existing issues and that they are important?
Do you need to collect more information?

## Slide 19
The more info you have, the more your project will target the problem and the more chance you will have an impact

## Slide 20: How do you develop a crime prevention project? What are the key elements?
2. Who does this affect? Identify a target group that is really AT-RISK, IN DIFFICULTY or GAINING STABILITY
It is important that you target one of these groups if you want to do ‘prevention’

## Slide 21: Target group is really AT-RISK, IN DIFFICULTY or GAINING STABILITY
At-risk
No crime committed
In difficulty
Crime has already been committed, have behavioural problems
Gaining stability
Crime committed in past
At-risk family life, lifestyle
Prevent from committing a crime or prevent from continuing to get into trouble
Showing behavioural problems
Could be at risk of reoffending, and or at risk of victimization
During sentencing: Identify opportunities for alternative measures, diversion programs
Prevent from committing another crime before, during or after sentencing
Need for support (social, professional, economic, etc.) or they could reoffend
Rehabilitation, reinsertion
Rehabilitation, reinsertion

## Slide 22: Target group is really AT-RISK, IN DIFFICULTY or GAINING STABILITY
  Make sure you can really recruit this group and that you choose the right group for your project

## Slide 23: Here is AN Example…
Youth gang problem in a community that is linked to the trafficking of drugs.
10 to 12 youth between the ages of 14-17 are involved and many more are at-risk of joining.
Info: Police, youth protection and social services data are used to understand this problem.
At-risk and in difficulty population: Participants are selected based on indicators such as aggressiveness, opposition, provocation, difficulties in social relations, behavioural problems, criminal record.
Risk factors: Low literacy, poor mental health, early and repeated anti-social behaviour.
We know that from other good practices from remote areas that a youth intervention and rehabilitation program works to prevent more youth from joining and help those in the gang.

## Slide 24: How do you develop a crime prevention project? What are the key elements?
3. Start to unpack the issue with the information you have so far

## Slide 25: Unpack the issue - The process
What is the problem? What information backs this up? | Risk factors that are causing the problem among your target group | Other reasons behind the problem | What is needed to prevent future problems?
There is a major problem of domestic violence against women when men are drinking. Statistics from police and social services show it is the #1 issue. At community meetings all main actors agree something needs to be done to address it. | - Substance abuse - Poor mental health - Unemployment | Small size and isolation of the community makes it difficult to find jobs, and there are few social services to provide mental health services People lack skills to get jobs and there is a high school drop-out rate | ???

## Slide 26: protective factors
What are the protective factors to address this issue?
-> What is needed to prevent the target group from committing a crime, being a victim or committing more crimes?

## Slide 27: Unpack the issue - The process
What is the problem? What information backs this up? | Risk factors that are causing the problem among your target group | Other reasons behind the problem | What is needed to prevent future problems?
There is a major problem of domestic violence against women when men are drinking. Statistics from police and social services show it is the #1 issue. At community meetings all main actors agree something needs to be done to address it. | - Substance abuse - Poor mental health - Unemployment | Small size and isolation of the community makes it difficult to find jobs, and there are few social services to provide mental health services People lack skills to get jobs and there is a high school drop-out rate | We specifically need: 2 social workers A women’s shelter Substance abuse treatment program for the men We want to prioritize for 2016: Training of 1 social worker Development of a substance abuse treatment program for the men

## Slide 28: Unpack the issue - The process
We want to prioritize for 2016:
Training of 1 social worker
Development of a substance abuse treatment program for the men
Unpack this further….
What type of social worker is needed?
What are the specifics of the program you want…what works elsewhere?

## Slide 29: How do you develop a crime prevention project? What are the key elements?
4. Identify goals, objectives, expected results. There needs to be a clear link between them, and they need to be achievable.
This helps you to see if you your project is well linked with the issue and can actually tackle it

## Slide 30
  Goal (what do you want to achieve, must be prevention of crime):
    Reduce youth gang related crimes
  Objectives (how to achieve your goal?):
    Develop an intervention and rehabilitation program to:
    a) Improve mental health and literacy ; and
    b) Reduce offending and anti-social behaviour.
    The program will offer educational services, psychological counselling and life skills training.
  Expected results
    Reduce offending and anti-social behaviour
    Increase school attendance and performance
    Improve mental health outcomes
    Reduce gang membership

## Slide 31: Clear link between risk factors, objectives, Results
Risk factors | Objectives | Expected results
Low literacy | Develop a intervention and rehabilitation program to improve literacy by providing a literacy program for target group | Increase school attendance and performance Reduce gang membership
Poor mental health | Develop a intervention and rehabilitation program to improve mental health by providing psychological counselling | Improve mental health outcomes Reduce offending and anti-social behaviour Reduce gang membership
Early and repeated anti-social behaviour | Develop a intervention and rehabilitation program to reduce offending and anti-social behaviour by providing a life skills training | Reduce offending and anti-social behaviour Reduce gang membership

## Slide 32: How do you develop a crime prevention project? What are the key elements?
5. Identify your project activities.
There needs to be a clear link between target group, risk factors, goals, objectives, project activities, and results.

## Slide 33: risk factors and oBJEctives help to develop Project activities
Risk factors | Objectives | Project activities
Low literacy | Develop a intervention and rehabilitation program to improve literacy | Set up a 30-week educational program at the adult education center for high-school drop-outs in the project
Poor mental health | Develop a intervention and rehabilitation program to improve mental health | Offer one-on-one psychological counselling services Provide referrals to a local healing program
Early and repeated anti-social behaviour | Develop a intervention and rehabilitation program to reduce offending and anti-social behaviour | Set up a 10-week life skills training

## Slide 34: How do you develop a crime prevention project? What are the key elements?
6. Identify partners and determine their roles and what resources they can share, gathering resources

## Slide 35: How do you develop a crime prevention project? What are the key elements?
7. Capacity

## Slide 36: How do you develop a crime prevention project? What are the key elements?
7. Capacity
What skills, goods, and services do you need for your project?
How will you get these skills, goods, and services?
Can you recruit some volunteers to help?
Determine if you will need to do any training.

## Slide 37: How do you develop a crime prevention project? What are the key elements?
  8. Monitor & Evaluate your project
  (also means to keep track of the implementation and performance of your project)
How will you know whether your project has been successful?

## Slide 38: For Those with existing projects
What information do you have about the issue your project is addressing?
  Have there been changes to the issues over time?
  Do you need to re-do your objectives and project activities to meet the changes?
Do you collect information about your project?
  If yes, have you used it to improve your project?

## Slide 39: For Those with existing projects
What challenges do you face in your project related to actually doing prevention?
What challenges do you face in your project related to capacity?
What challenges do you face in developing for the long-term?

## Slide 40: For Those with existing projects
  Do you know for sure that your project has had an impact?
If your project has been running for many years, you should consider getting an external evaluation.
If you’ve done an evaluation, did you implement the recommendations to improve the project?